## Text
The junction will be constructed at the end of or after the current programme for Principal Street and therefore that the footpaths will be as permanent construction.
2-Way temporary traffic signals for a period of 8 weeks only
No permanent highway boundary fence included
Allowed for 4nr new gully’s & outfall into drainage ditches
Estimated costs for new street lighting now included
Made allowance for ducting, chambers, loop boxes & sockets for the traffic signals and typical costs for Siemens to install heads now including pedestrian phases and loops
The 600 & 700 series quantities allow for the following full carriageway construction depths from the drawing 700/01:
40mm surf
60mm binder
150mm base
350mm sub base
550mm capping
Included to remove and relay the existing binder and surface course,
No allowance for services but we suspect a BT and Gas Diversion will be required and need 2-3 months notice
Assumptions made without seeing any design information

## Budget
Item | Description | Quantity | Unit | 2022 Budget Value | Value
| Series 150 TRAFFIC MANAGEMENT | 1 | Item | 8400 | 8400
| Series 200 SITE CLEARANCE | 1 | Item | 2300 | 2300
| Series 300 FENCING | 1 | Item | 922 | 922
| Series 500 DRAINAGE AND SERVICE DUCTS | 1 | Item | 40000 | 40000
| Series 600 EARTHWORKS | 1 | Item | 90000 | 90000
| Series 700 PAVEMENTS | 1 | Item | 106000 | 106000
| Series 1100 KERBS, FOOTWAYS AND BLOCK PAVED AREAS | 1 | Item | 60000 | 60000
| Series 1200 TRAFFIC SIGNS AND ROAD MARKING | 1 | Item | 8000 | 8000
| Series 1400 ELECTRICAL WORK FOR ROAD LIGHTING AND TRAFFIC SIGNS | 1 | Item | 110000 | 110000
| Series 3000 LANDSCAPE AND ECOLOGY | 1 | Item | 5000 | 5000
| Suggested Prelims for Management and Welfare | 1 | Item | 55000 | 55000
485622